## 15Mar-21Mar
WSR Period - 06-Sep to 12-Sep (Saturday to Friday)
Current Week's work
Sprint Name / Number | Sprint Start Date | Sprint End Date | Jira ID | Description | Status | Due Date | Actual Completion Date | Story Points of the Story/Task
22 | 2025-08-29 | 2025-09-12 | GP-2022 | Add Extra ServiceNow Tooling | Ready for QA
22 | 2025-08-29 | 2025-09-12 | GP-2783 | Jira Tool: Jira Update Issue fails to update Tested By Field | Ready for QA
22 | 2025-08-29 | 2025-09-12 | GP-2781 | Jira tool: jira update issue fails to update Component | Ready for QA
22 | 2025-08-29 | 2025-09-12 | GP-2503 | Jira tool: jira update issue fails to update epic | Ready for QA
22 | 2025-08-29 | 2025-09-12 | GP-2792 | get_transition: error | VERIFIED
22 | 2025-08-29 | 2025-09-12 | GP-2803 | JIRA eVestment: jira create issue- In chat response web URL has API | VERIFIED
22 | 2025-08-29 | 2025-09-12 | GP-2805 | jira_get_creation_fields tool does not return all allowed values | In Progress
22 | 2025-08-29 | 2025-09-12 | GP-2798 | Knowledge Base Management Tools | In Progress
22 | 2025-08-29 | 2025-09-12 | GP-2795 | Add worklog: interpretation of weeks and days is strange | In Progress
Next Week's planned work (if any)
Sprint Name / Number | Sprint Start Date | Sprint End Date | Jira ID | Description | Status | Due Date | Actual Completion Date | Story Points of the Story/Task
Work Hours and Leaves
Work Hours (Saturday to Friday) - 0-0-8-8-8-8-8
Leaves (Current Week): NA
Leaves (Next 2 weeks): NA
Impediments/Dependency/Support required:
Imepdiment: NA
Dependency - NA
Support Required - NA
Approeciation received / Concern raised on your work
Appreciation: NA
Concern - NA
[8 empty] | GP-2022 | Add Extra ServiceNow Tooling
[8 empty] | GP-2183 | ServiceNow: add possibility to filter articles on multiple fields (author, published date, etc)
[8 empty] | GP-2182 | Splunk alert for stackoverflow connector
[8 empty] | GP-2117 | ServiceNow unable to query for articles
[8 empty] | GP-2175 | ServiceNow: add 'number' as return parameter
[8 empty] | GP-2144 | ServiceNow list_article: add article id as part of return
[8 empty] | GP-2131 | ServiceNow error on filtering incidents when there are not enough incidents to meet the requested number - multiple users with the same name
[8 empty] | GP-2096 | ServiceNow list articles pagination error
[8 empty] | GP-2118 | ServiceNow unable to list incidents with priority parameter
[8 empty] | GP-2115 | ServiceNow unable to get articles with knowledge base filter
[8 empty] | GP-2114 | ServiceNow unable to get incidents seen through the frontend of instance
[8 empty] | GP-2133 | ServiceNow unable to get incidents based on state
[8 empty] | GP-2153 | Servicenow: number of incidents received doesn't match the request, although there are enough incidents that match the criteria
[8 empty] | GP-2142 | ServiceNow Knowledge base max count is wrong
[8 empty] | GP-2085 | ServiceNow response error observed for getting certain articles
[8 empty] | GP-2134 | ServiceNow unable to get incidents based on assignee
[8 empty] | GP-2020 | Troubleshoot ServiceNow Tooling
[8 empty] | GP-2095 | ServiceNow list calls do not return expected results